## Sheet1
Risk | Risk Statement | Response stratergy | Objectives | Initial |  |  | second |  |  | third |  |  | Final |  |  | Final
|  |  |  | Likelyhood | Impact | Risk Level | likelyhood | impact | Risk level | likelyhood | impact | Risk Level | Likelyhood | Impact | Risk Level | Likelyhood | Impact | Risk Level
Kubernetes networking unsuccessful | The application wouldn't be able to deploy | understand how k8s works | kubernetes enables the app to run | high | high | 70 % | high | high | 40 % | medium | high | 20 %
Exceeding the budget | The CI pipeline | use cost effective resources for deployment | keep the cost of deployment low | high | high | 70 % | high | high | 70 % | low | high | 10 %
Exceeding the time limit | If we go over the time limit then the project will not pass | Make sure I am implementing the features | include all the crud features | low | high | 20 % | low | high | 20 % | low | high | 10 %
Exposed keys | if keys are exposed , unauthorised access could occur | maintain that best practises are used for version control | maintain that best practises are used | high | high | 70 % | high | high | 70 % | medium | high | 10 %
Branch conflicts | too many merge conflicts and deployment will be halted | push working versions of code on to the master | export the secret key | high | medium | 80 % | medium | medium | 50 % | low | medium | 10 %
Jenkins password exposed | if jenkins is exposed the app would be vunerable | use best practices to keep passwords secure | ensure password is not exposed | high | medium | 80 % | high | medium | 50 % | high | medium | 10 %
AWS sever exposed | if exposed there is a risk that the app could be deleted | make sure users with access are authorised | Make IAM Users for team members only | high | medium | 80 % | high | medium | 70 % | medium | medium | 10 %
docker images not updating | if docker images arent updated the app doesnt run | make sure that docker and git are linked together | automated builds can be performed | high | medium | 80 % | high | medium | 70 % | medium | medium | 10 % | [5 empty] | 10%
Jenkins pipeline | if this occurs the app wont run correctly | add a github webhook | Have a webhook that works